## Slide 1: Origins Space Telescope (OST) Face-to-Face #5 Study Office
June 14-15, 2017
Ruth.C.Carter@nasa.gov
1

## Slide 2: Study Office Status/Plan
Held the Kick-off meeting with Ball Consortium on April 20, 2017 at GSFC
Completed instrument design sessions for three instruments
  Far-IR Imaging Polarimeter (FIP) completed IDL (4/17-21): Johannes Staguhn/PI
  High Resolutions Spectrometer (HRS) completed IDL (5/1-5): Harvey Moseley/PI
  Medium Resolutions Survey Spectrometer (MRSS, JPL) completed Team-X run (5/8-11): Matt Bradford/PI
Maximized space in the optical bench and Instrument Accommodation Module (IAM) to house all five instruments
  IAM will also house secondary, tertiary and Field Steering Mirror (FSM)
Added 20K thermal zone for the OST Observatory concept to facilitate thermal management for instruments
Redesigned sun shields to minimize solar pressure issue
  Sun shields are no longer flat, rather they are nested “sugar-scoop” shape

## Slide 3: Study Office Status/Plan - continued
Potential additional contribution from JPL is in discussion
  JPL’s active mirror concept can be the OST’s Primary Mirror for the telescope
Remaining Design Sessions for fiscal year 2017 are:
  Instrument Accommodation Module (IAM) IDL scheduled for July 17 through 21
  Telescope System IDL scheduled for August 14 through 23
  End-to-End Concept 1 mission design MDL scheduled for September 18 through 27
Plan to complete Concept 1 mission design by September 30, 2017
Independent Technical Review (ITR) is scheduled for October 25-26 at NASA GSFC
  OST science for Concept 1
  Concept 1 mission design
Interim Report due to HQ on December 15, 2017
  OST Science and Mission Design Concept 1 are expected to be addressed in the interim report

## Slide 4: Study Schedule